## LCM Job Card
# | Sample Job Card | Soumyadeep P | Akash P | Gaurav M | Ankit O | Pranav Y | Aditya S | Shrawani M | Apeksha S | Sneha B | Rahi M | Vanshika G | Ruhikesh N | Nitish K | Tanvi B | Chandrashekhar L | Open | Close
1 | Trade Booking
a | Book Trade 1-10 |  |  |  | 1 | [11 empty] | 2026-06-02 | 2026-06-03
b | Book Trade 11-20 |  |  |  |  | 1 | [10 empty] | 2026-06-02 | 2026-06-03
c | Book Trade 21-30 | [5 empty] | 1 | [9 empty] | 2026-06-02 | 2026-06-03
d | Book Trade 31-40 | [10 empty] | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
e | Book Trade 41-50 | [10 empty] | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
f | Book Trade 51-60 | 1 | [14 empty] | 2026-06-02 | 2026-06-03
g | Book Trade 61-70 |  |  |  |  | 1 | [10 empty] | 2026-06-02 | 2026-06-03
h | Book Trade 71-80 |  |  |  | 1 | [11 empty] | 2026-06-02 | 2026-06-03
j | Book Trade 81-90 | [5 empty] | 1 |  |  |  | 2 | [5 empty] | 2026-06-02 | 2026-06-03
i | Book Trade 91-100 | [8 empty] | 1 | [6 empty] | 2026-06-02 | 2026-06-03
1 | Trade Checking
a | Check Trade 1-10 | [6 empty] | 1 | [8 empty] | 2026-06-02 | 2026-06-03
b | Check Trade 11-20 | [7 empty] | 1 | [7 empty] | 2026-06-02 | 2026-06-03
c | Check Trade 21-30 | [8 empty] | 1 | [6 empty] | 2026-06-02 | 2026-06-03
d | Check Trade 31-40 | [10 empty] | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
e | Check Trade 41-50 |  |  |  |  | 1 | [10 empty] | 2026-06-02 | 2026-06-03
f | Check Trade 51-60 | [5 empty] | 1 | [9 empty] | 2026-06-02 | 2026-06-03
g | Check Trade 61-70 | [8 empty] | 1 | [6 empty] | 2026-06-02 | 2026-06-03
h | Check Trade 71-80 | [10 empty] | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
j | Check Trade 81-90 | 1 | [14 empty] | 2026-06-02 | 2026-06-03
i | Check Trade 91-100 |  |  |  | 1 | [11 empty] | 2026-06-02 | 2026-06-03
2 | Test Setup (LCM)
a | Test User Creations |  |  |  |  | 1 | 2 | [9 empty] | 2026-05-28 | 2026-06-02
b | Product Rules Configuration for FCN |  |  |  |  | 1 | 2 | [9 empty] | 2026-05-28 | 2026-06-01
c | Product Rules Configuration for AQ |  |  |  |  | 1 | 2 | [9 empty] | 2026-05-28 | 2026-06-01
d | Product Rules Configuration for DQ |  |  |  |  | 1 | 2 | [9 empty] | 2026-05-28 | 2026-06-01
e | Fixing Prices Update for underlyings |  |  |  |  | 1 | 2 | [9 empty] | 2026-05-28 | 2026-06-01
b | Underlying prices setup | 2 |  |  | 3 | [6 empty] | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
C | Workflow Blotter Setup for New entity | [8 empty] | 2 |  | 1 |  |  |  |  | 2026-06-02 | 2026-06-03
d | Lifecycle event process batch setup |  | 1 | 2 | [12 empty] | 2026-05-28 | 2026-06-01
e | Start-of-day setup |  | 2 | 1 | [12 empty] | 2026-06-02 | 2026-06-04
f | ISIN Snapshot setup |  | 1 | 2 | [12 empty] | 2026-06-02 | 2026-06-04
g | Event Calendar setup |  | 2 | 1 | [12 empty] | 2026-06-02 | 2026-06-04
3 | Verification (LCM)
a | Start-of-date | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
b | ISIN Snapshot | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
c | Event Calendar | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
d | FCN Rules | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
e | AQ Rules | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
f | DQ Rules | [11 empty] | 1 | 2 |  |  | 2026-06-04 | 2026-06-05
4 | Product Setup
| MetadataFunction Script |  |  |  |  | 1 | [10 empty] | 2026-06-11 | 2026-06-15
| MetadataScript |  |  |  | 1 | [11 empty] | 2026-06-11 | 2026-06-15
| FilterFunction | 1 | [14 empty] | 2026-06-11 | 2026-06-15
| ActionFunction | [5 empty] | 1 | [9 empty] | 2026-06-11 | 2026-06-15 | Done
| LCM Testing | 1 | [5 empty] | 1 |  | 1 | 1 | 1 |  |  |  |  | 2026-06-11 | 2026-06-15 | Due
| AQ/DQ Product Flow SS and narration | 1 | [5 empty] | 1 | [8 empty] | 2026-06-10 | 2026-06-11 | Half-Done
| FCN Product Flow SS and narration | 1 | [8 empty] | 1 | [5 empty] | 2026-06-10 | 2026-06-15 | Redo
| TRS Product Flow SS and narration | 1 | [5 empty] | 1 |  | 1 | 1 | 1 |  |  |  |  | 2026-06-15 | 2026-06-15 | Late
| Laka Tiles Setup | [15 empty] | 2026-06-11 | 2026-06-10 | On hold
| Global Product Calendar UI development | [13 empty] | 1 | 2 | 2026-06-08 | 2026-06-16 | Almost ready
| Deployment Testing | [7 empty] | 1 | [7 empty] | 2024-07-28 | 2024-07-31 | Just started
| Deployment Testing | [7 empty] | 1 | [7 empty] | 2024-07-28 | 2024-07-31 | NA